## Sheet1
ALBUQUERQUE PUBLIC SCHOOLS - WHERRY ELEMENTARY SCHOOL
PERFORMANCE REPORT BUDGET COMPARISON
Budget Category | Grant Budget | Period 1 |  |  | Period 2 |  |  | Period 3 |  |  | Period 4 |  |  | Balance Remaining | OEA Exp to Date
|  | 5/01/13 - 3/31/14 |  |  | 4/01/14 to 6/30/14 |  |  | 7/01/14 to 9/30/14 |  |  | 10/01/14 to 12/31/14
|  | OEA | Match | Total | OEA | Match | Total | OEA | Match | Total | OEA | Match | Total
1. Administrative | 57406 |  | 15406 | 15406 |  |  | 0 |  |  | 0 |  |  | 0 | 42000 | 0
2. Land, structures, rights-of-way, appraisals, etc. | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0
3. Relocation exp. | 776078 |  | 68078 | 68078 |  |  | 0 |  |  | 0 |  |  | 0 | 708000 | 0
4. A/E Basic | 1573781 |  | 471150 | 471150 | 92853.72 |  | 92853.72 | 238072.82 |  | 238072.82 | 153716.32 |  | 153716.32 | 617988.14 | 484642.86
5. Other A/E | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0
6. Project Inspect. | 163819 |  | 23819 | 23819 |  |  | 0 |  |  | 0 |  |  | 0 | 140000 | 0
7. Site Work | 1307290 |  | 53841 | 53841 |  |  | 0 |  |  | 0 |  |  | 0 | 1253449 | 0
8. Demo | 202037 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 202037 | 0
9. Construction | 11333329 |  | 2455496 | 2455496 |  |  | 0 |  |  | 0 |  |  | 0 | 8877833 | 0
10. Equipment | 1993413 |  | 278413 | 278413 |  |  | 0 |  |  | 0 |  |  | 0 | 1715000 | 0
11. Misc | 1063120 |  |  | 0 |  |  | 0 | 28088.32 |  | 28088.32 | 20106.44 |  | 20106.44 | 1014925.24 | 48194.76
12. Contingencies | 1145930 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1145930 | 0
PROJECT TOTAL | 19616203 | 0 | 3366203 | 3366203 | 92853.72 | 0 | 92853.72 | 266161.14 | 0 | 266161.14 | 173822.76 | 0 | 173822.76 | 15717162.38 | 532837.62
Federal Share | 16250000 | [12 empty] | 15717162.38
Match | 3366203 | [12 empty] | 0
Match % |  |  | #DIV/0! |  |  | 0% |  |  | 0% |  |  | 0%
Budget Category | Grant Budget (from 5/01/13 - 12/31/14 period) | Period 5 |  |  | Period 6 |  |  | Period 7 |  |  | Period 8 |  |  | Balance Remaining
|  | 01/01/15 to 3/31/15 |  |  | 4/01/15 to 6/30/15 |  |  | 7/01/15 to 9/30/15 |  |  | 10/01/15 to 12/31/15 |  |  |  | OEA Exp to Date
|  | OEA | Match | Total | OEA | Match | Total | OEA | Match | Total | OEA | Match | Total
1. Administrative | 42000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 42000 | 0
2. Land, structures, rights-of-way, appraisals, etc. | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
3. Relocation exp. | 708000 | 34111.66 |  | 34111.66 | 262956.89 |  | 262956.89 |  |  | 0 |  |  | 0 | 410931.45 | 297068.55
4. A/E Basic | 617988.14 | 62611.27 |  | 62611.27 | 15971.49 |  | 15971.49 | 21482.88 |  | 21482.88 | 26440.45 |  | 26440.45 | 491482.05 | 611148.95
5. Other A/E | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0
6. Project Inspect. | 140000 |  |  | 0 |  |  | 0 | 10823.26 |  | 10823.26 | 9817.84 |  | 9817.84 | 119358.9 | 20641.1
7. Site Work | 1253449 | 20730.71 |  | 20730.71 | 227.38 |  | 227.38 | 11730 |  | 11730 | 2297.03 |  | 2297.03 | 1218463.88 | 34985.12
8. Demo | 202037 |  |  | 0 | 48777.51 |  | 48777.51 |  |  | 0 |  |  | 0 | 153259.49 | 48777.51
9. Construction | 8877833 |  |  | 0 |  |  | 0 | 863719 |  | 863719 | 1214376 |  | 1214376 | 6799738 | 2078095
10. Equipment | 1715000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1715000 | 0
11. Misc | 1014925.24 | 28743.56 |  | 28743.56 | 24752.92 |  | 24752.92 | 12226.57 |  | 12226.57 | 12032.03 |  | 12032.03 | 937170.16 | 125949.84
12. Contingencies | 1145930 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1145930 | 0
PROJECT TOTAL | 15717162.38 | 146197.2 | 0 | 146197.2 | 352686.19 | 0 | 352686.19 | 919981.71 | 0 | 919981.71 | 1264963.35 | 0 | 1264963.35 | 13033333.93 | 3216666.07
Federal Share | 15717162.38 | [12 empty] | 13033333.93
Match | 0 | [12 empty] | 0
Match % |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Budget Category | Grant Budget (from 1/01/15 - 12/31/15 period) | Period 9 |  |  | Period 10 |  |  | Period 11 |  |  | Period 12 |  |  | Balance Remaining
|  | 1/01/16 to 3/31/16 |  |  | 4/01/16 to 6/30/16 |  |  | 7/01/16 to 9/30/16 |  |  | 10/01/16 to 12/31/16 |  |  |  | OEA Exp to Date
|  | OEA | Match | Total | OEA | Match | Total | OEA | Match | Total | OEA | Match | Total
1. Administrative | 42000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 42000 | 0
2. Land, structures, rights-of-way, appraisals, etc. | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
3. Relocation exp. | 410931.45 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 410931.45 | 297068.55
4. A/E Basic | 491482.05 | 25899.84 |  | 25899.84 |  |  | 0 |  |  | 0 |  |  | 0 | 465582.21 | 637048.79
5. Other A/E | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0
6. Project Inspect. | 119358.9 | 4507.24 |  | 4507.24 |  |  | 0 |  |  | 0 |  |  | 0 | 114851.66 | 25148.34
7. Site Work | 1218463.88 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1218463.88 | 34985.12
8. Demo | 153259.49 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 153259.49 | 48777.51
9. Construction | 6799738 | 1762870 |  | 1762870 |  |  | 0 |  |  | 0 |  |  | 0 | 5036868 | 3840965
10. Equipment | 1715000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1715000 | 0
11. Misc | 937170.16 | 12376.64 |  | 12376.64 |  |  | 0 |  |  | 0 |  |  | 0 | 924793.52 | 138326.48
12. Contingencies | 1145930 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1145930 | 0
PROJECT TOTAL | 13033333.93 | 1805653.72 | 0 | 1805653.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11227680.21 | 5022319.79
Federal Share | 13033333.93 | [12 empty] | 11227680.21
Match | 0 | [12 empty] | 0
Match % |  |  | 0% |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0!
Budget Category | Grant Budget (from 1/01/16 - 12/31/16 period) | Period 13 |  |  | Period 14 |  |  | Period 15 |  |  | Period 16 |  |  | Balance Remaining
|  | 1/01/17 to 3/31/17 |  |  | 4/01/17 to 6/30/17 |  |  | 7/01/17 to 9/30/17 |  |  | 10/01/17 to 12/31/17 |  |  |  | OEA Exp to Date
|  | OEA | Match | Total | OEA | Match | Total | OEA | Match | Total | OEA | Match | Total
1. Administrative | 42000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 42000 | 0
2. Land, structures, rights-of-way, appraisals, etc. | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0
3. Relocation exp. | 410931.45 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 410931.45 | 297068.55
4. A/E Basic | 465582.21 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 465582.21 | 637048.79
5. Other A/E | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0
6. Project Inspect. | 114851.66 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 114851.66 | 25148.34
7. Site Work | 1218463.88 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1218463.88 | 34985.12
8. Demo | 153259.49 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 153259.49 | 48777.51
9. Construction | 5036868 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 5036868 | 3840965
10. Equipment | 1715000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1715000 | 0
11. Misc | 924793.52 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 924793.52 | 138326.48
12. Contingencies | 1145930 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1145930 | 0
PROJECT TOTAL | 11227680.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11227680.21 | 5022319.79
Federal Share | 11227680.21 | [12 empty] | 11227680.21
Match | 0 | [12 empty] | 0
Match % |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0!
Budget Category | Grant Budget (from 1/01/16 - 12/31/16 period) | Period 18 |  |  | Balance Remaining
|  | 1/01/17 to 3/31/17 |  |  |  | OEA Exp to Date
|  | OEA | Match | Total
1. Administrative | 42000 |  |  | 0 | 42000 | 0
2. Land, structures, rights-of-way, appraisals, etc. | 0 |  |  | 0 | 0 | 0
3. Relocation exp. | 410931.45 |  |  | 0 | 410931.45 | 297068.55
4. A/E Basic | 465582.21 |  |  | 0 | 465582.21 | 637048.79
5. Other A/E | 0 |  |  | 0 | 0 | 0
6. Project Inspect. | 114851.66 |  |  | 0 | 114851.66 | 25148.34
7. Site Work | 1218463.88 |  |  | 0 | 1218463.88 | 34985.12
8. Demo | 153259.49 |  |  | 0 | 153259.49 | 48777.51
9. Construction | 5036868 |  |  | 0 | 5036868 | 3840965
10. Equipment | 1715000 |  |  | 0 | 1715000 | 0
11. Misc | 924793.52 |  |  | 0 | 924793.52 | 138326.48
12. Contingencies | 1145930 |  |  | 0 | 1145930 | 0
PROJECT TOTAL | 11227680.21 | 0 | 0 | 0 | 11227680.21 | 5022319.79
Federal Share | 11227680.21 |  |  |  | 11227680.21
Match | 0 |  |  |  | 0
Match % |  |  | #DIV/0!

## Sheet2
| OEA Period | Dates | Billing | Lawson | Errors
School Year F14 Q3 | 1 | 5/1/13-3/31/14 | 0 | 0 | 0
School Year F14 Q4 | 2 | 4/1/14-6/30/14 | 92853.72 | 92853.72 | 0
School Year F15 Q1 | 3 | 7/1/14-9/30/14 | 266161.14 | 266161.14 | 0
School Year F15 Q2 | 4 | 10/1/14-12/31/14 | 173822.76 | 173822.76 | 0
School Year F15 Q3 | 5 | 1/1/15-3/31/15 | 146197.2 | 146197.2 | 0
School Year F15 Q4 | 6 | 4/1/15-6/30/15 | 352686.19 | 352686.19 | 0
School Year F16 Q1 | 7 | 7/1/15-9/30/15 | 919981.71 | 919981.71 | 0
School Year F16 Q2 | 8 | 10/1/15-12/31/15 | 1264963.35 | 1264963.35 | 0
School Year F16 Q3 | 9 | 1/1/16-3/31/16 | 1805653.72 |  | 1805653.72
School Year F16 Q4 | 10 | 4/1/16-6/30/16 | 0 |  | 0
School Year F17 Q1 | 11 | 7/1/16-9/30/16 | 0 |  | 0
School Year F17 Q2 | 12 | 10/1/16-12/31/16 | 0 |  | 0
School Year F17 Q3 | 13 | 1/1/17-3/31/17 | 0 |  | 0
School Year F17 Q4 | 14 | 4/1/17-6/30/17 | 0 |  | 0
School Year F18 Q1 | 15 | 7/1/17-9/30/17 | 0 |  | 0
School Year F18 Q2 | 16 | 10/1/17-12/31/17 | 0 |  | 0
|  |  | 5022319.79 | 3216666.07 | 1805653.72